## Tasks
Task Name | Start Time | Duration
CloudGuard Agent | 2026-10-07 | 52
To-do |  | 1
Set up a dedicated GCP Sandbox project for your development. | 2026-10-19 | 1
Enable the necessary APIs: Security Command Center, Pub/Sub, Cloud Functions, Firestore, and Vertex AI. | 2026-10-19 | 1
Configure SCC Enterprise in your sandbox environment. | 2026-10-19 | 5
Set up a Continuous Export in SCC to route findings directly to a Cloud Pub/Sub topic. | 2026-10-19 | 5
Apply filters to the export so only specific, active findings (e.g., state="ACTIVE" AND severity="HIGH") trigger messages. | 2026-10-19 | 5
Intentionally misconfigure a resource and verify the JSON payload arrives in Pub/Sub with the built-in Gemini context included. | 2026-10-19 | 5
Create a Pub/Sub subscription that streams events directly into BigQuery. | 2026-10-19 | 5
Write a Python Cloud Function triggered by the Pub/Sub topic. | 2026-10-19 | 5
Create a Pub/Sub subscription to trigger your initial Cloud Function. | 2026-10-19 | 5
Integrate Firestore into your Cloud Function. | 2026-10-26 | 5
Integrate the Google Chat API. Send a formatted UI card containing the SCC built-in threat summary and interactive buttons (e.g., [Acknowledge], [Generate PR]). | 2026-10-26 | 5
Format the Cloud Function output into an interactive UI card. The card should display: The AI-generated threat summary from SCC. A code block containing the generated Terraform code. Interactive buttons (e.g., [Acknowledge], [Mark as False Positive]). | 2026-11-02 | 5
Create a Google Chat webhook integration. | 2026-11-02 | 5
Build a webhook receiver (Cloud Run) to handle button clicks from the chat interface. When a user clicks [Acknowledge], update the Firestore document so the alert is silenced. | 2026-11-02 | 5
Extract the built-in Gemini threat summary and remediation steps from the SCC JSON payload. | 2026-11-02 | 5
Pass those remediation steps into the Vertex AI API (Gemini Pro) with a strict system prompt: "You are a DevSecOps engineer. Translate these remediation steps into valid Terraform (HCL) code. Output ONLY the Terraform block." | 2026-11-02 | 5
Add Git API logic to your Cloud Run service to branch the repo, commit the Terraform block, and open a Pull Request. | 2026-11-09 | 5
Update the Firestore document status to PR_OPEN. | 2026-11-09 | 5
Send an asynchronous confirmation message back to the Google Chat thread with the PR link. | 2026-11-09 | 5
Trigger multiple different misconfigurations and monitor the end-to-end flow. | 2026-11-16 | 5
Review the generated Terraform. Is it accurate? Does it use the correct provider syntax? Tweak the Vertex AI prompt to improve the HCL formatting. | 2026-11-16 | 5
Connect Looker Studio to your BigQuery dataset to build a quick dashboard showing "Total Vulnerabilities Detected" and "Mean Time to Action". | 2026-11-16 | 5
Test edge cases (e.g., what happens if SCC triggers the same alert twice in one minute?). | 2026-11-16 | 5
Create a short slide deck summarizing the architecture and the GCP services used. | 2026-11-23 | 5
Prepare your demo script. Focus on the business value: saving time and enforcing Infrastructure as Code best practices. | 2026-11-23 | 5
Crucial: Record a video of the system working flawlessly. Live demos can break due to network issues or API delays; having a backup video guarantees success. | 2026-11-23 | 5
Practice the live run-through. | 2026-11-23 | 5
Doing |  | 1
Done |  | 1
Design the Firestore database schema for tracking alert states (e.g., alert_id, status, timestamp) to prevent duplicate notifications. | 2026-10-12 | 5
Create the BigQuery dataset and table schema for long-term analytics. | 2026-10-12 | 5
Create a detailed architecture diagram (SCC -> Pub/Sub -> Cloud Function -> Vertex AI -> Chat API -> Firestore). | 2026-10-12 | 5
Research SCC Enterprise's built-in Gemini capabilities (e.g., how it summarizes misconfigurations and suggests remediations). | 2026-10-07 | 3
Draft the user journey from the perspective of the security engineer receiving the Chat alert. | 2026-10-07 | 3