## Risk Register
Risk ID | Category | Risk Title & Description | Root Cause / Trigger | Initial Impact (1-5) | Initial Likelihood (1-5) | Initial Score | Mitigation Strategy & Preventative Control | Contingency Plan | Owner | Residual Impact (1-5) | Residual Likelihood (1-5) | Residual Score | Status
RSK-01 | Architecture & AI | AI Agent Generates Invalid or Deprecated Terraform HCL Syntax | LLM outputting hallucinated arguments, outdated provider syntax, or missing required attributes for GCP resources. | 4 | 4 | 16 | Implement recursive code-validation loop in Cloud Run harness: agent runs 'terraform validate' and syntax linters in a loop to self-correct before opening the PR. | Fallback to pre-validated deterministic HCL templates for the 3 demo resource types. | Lead Engineer | 2 | 2 | 4 | Mitigated
RSK-02 | Cloud & Infrastructure | Google Chat Webhook 504 Timeout During Multi-Step Agent Reasoning | Google Chat expects HTTP 200 within 3-5 seconds; Cloud Run cold starts + multi-step Agent reasoning take 8-15 seconds. | 4 | 4 | 16 | Asynchronously decouple webhook: immediately return HTTP 200 with an ephemeral 'Generating fix...' card, then post final PR card via Chat API once ready. | Cloud Run timeout fallback posts status update to Chat and triggers async retry. | Lead Engineer | 3 | 1 | 3 | Mitigated
RSK-03 | Project & Licensing | SCC Enterprise Tier / Built-in Gemini Unavailable in Sandbox | GCP Sandbox environment lacks paid Enterprise licenses or org-level IAM permissions for native Gemini summaries. | 4 | 3 | 12 | Design pipeline to accept standard SCC findings and fall back to Agent-driven summarization; maintain canned realistic JSON test fixtures. | Replay captured production SCC JSON events directly to Pub/Sub via mock publisher script. | Lead Engineer / Anthony | 3 | 1 | 3 | Active
RSK-04 | Architecture & State | Pub/Sub At-Least-Once Delivery Causes Duplicate Chat Spam | Pub/Sub message re-delivery or repeat scanner executions generating multiple alerts for the same ongoing vulnerability. | 3 | 4 | 12 | Strict O(1) idempotent deduplication in Firestore using SCC finding.name as Document ID; discard alerts if status is NOTIFIED, ACKNOWLEDGED, or PR_OPEN. | Apply Firestore 1-hour silence window TTL to suppress repeat notifications. | Lead Engineer | 2 | 1 | 2 | Mitigated
RSK-05 | Cloud & Operations | Alert Storm Overwhelms Agent Rate Limits & Causes Cost Spikes | Bulk GCP resource misconfigurations trigger hundreds of simultaneous alerts, hitting Vertex AI 429 quota limits. | 3 | 3 | 9 | Apply SQL-like export filters in SCC (state='ACTIVE' AND severity='HIGH'); configure Pub/Sub flow control (max 5 outstanding messages) and Cloud Function concurrency limits. | Route overflow messages to a dead-letter topic (DLQ) with exponential backoff processing. | Lead Engineer | 3 | 1 | 3 | Mitigated
RSK-06 | Architecture & DevOps | Terraform State Drift from Manual Out-of-Band Console Fixes | Resource modified directly in GCP Console while PR is pending, desynchronizing the live environment from Git repository state. | 4 | 3 | 12 | Strict GitOps enforcement: bot only opens Pull Requests (no unilateral direct execution); CI pipeline runs 'terraform plan' during PR creation to catch drift. | PR reviewer verifies drift warnings before approving merge; re-runs planning if out-of-sync. | Lead Engineer | 2 | 2 | 4 | Mitigated
RSK-07 | Architecture & Data | Dual-Write Inconsistency Between Firestore and BigQuery | Cloud Function crash or transient BigQuery API timeout after updating Firestore, causing analytics divergence from live state. | 3 | 3 | 9 | Leverage native Pub/Sub-to-BigQuery streaming subscription for the analytical audit trail; Firestore handles isolated transactional state updates. | Periodic reconciliation query comparing Firestore document states against BigQuery latest snapshots. | Lead Engineer | 3 | 1 | 3 | Monitoring
RSK-08 | Security & Governance | Bot Token / Service Account Credential Exposure | Git personal access tokens or service account keys accidentally logged or hardcoded in repositories. | 5 | 2 | 10 | Store bot credentials in GCP Secret Manager; enforce least-privilege IAM roles (scoped to target repo PR creation only; no branch deletion or admin rights). | Automated Secret Manager secret rotation and immediate token invalidation procedure. | Lead Engineer | 2 | 1 | 2 | Mitigated
RSK-09 | Project & Demo Execution | Live Demo Failure Due to API Delays or Network Interruption | Presentation venue network lag, SCC scan propagation delay (2-5 mins), or transient GCP API latency during presentation. | 5 | 2 | 10 | Record a pristine, high-definition end-to-end screencast video during Week 8; build an offline fixture replay mode. | Instantly switch to high-resolution backup recording with live narration if API response takes >10 seconds. | Lead Engineer | 2 | 1 | 2 | Mitigated
RSK-10 | Project Management | Scope Creep Overwhelming 8-Week Graduate Capstone Timeline | Attempting to build multi-cloud remediations, complex custom web dashboards, or excessive finding categories. | 4 | 3 | 12 | Freeze scope to 3 high-impact GCP misconfigurations (Public Cloud Storage Bucket, Open SSH Firewall, Overprivileged IAM) and utilize BigQuery Canvas / Google Chat cards. | Focus strictly on the core alert-to-PR loop as MVP; document additional features as future roadmap extensions. | Lead Engineer | 3 | 1 | 3 | Closed